## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% | 63.16% | 21.05% | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 4 mi | 66.67% | 40% | 26.67% | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi | 0 mi | 50% | 0% | 50% | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% | 40.91% | 31.82% | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi | 30 mi | 44.12% | 30% | 8.824% | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 | 2 | 2 | 40% | 40% | 0% | No new substations completed. Delay in electrical components impacts schedule.

## Sheet1
Financials
| Actual Expenditure | Expected Over-budget
Eastern Section | 90000000 | 125000000

## Dashboard
Metroville Urban Rail Expansion Project Dashboard
| Display here main numbers/KPI of the overall project |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Phase 1
[5 empty] | Phase 2 | [6 empty] | ←Illustrative
Phase 3
Phase 4
PHASE 1
| Progress - Completion % | [8 empty] | Project Financials
| Status Update |  | Challenges
| 6mi of electrification completed in Eastern section, bringing total electrified distance to 30mi, out of the 68 miles planned. 4mi of track laying completed for Southeastern Quadrant, having done 10mi out of 15 planned miles. Eastern Section has no improvement of track installation as it is left with 6 miles same as previous week, out of planned 12 miles. |  | - Eastern section in risk - Delay due to rocky terrain - 6mi behind schedule ACTION: in progress evaluation of alternative method to expedite progress. - Overspent in the excavation ACTION: Savings on materials have offset this, keeping us within 5% of our overall budget projection for this phase. - Substations construction: Delay in electrical components ACTION: action plan in progress with Buyer
| Community Feedback Highlights |  |  | Noise Pollution concern raised by the residents in Eastern Section due to night-time constructions, No progress of track layout for Eastern section.
Positive feedback on engagement, community engagement is well-received and appreciated for the transparency and opportunity to voice their concerns.
Noise concerns: Night time working in Eastern Setion creating noise, residents requesting to keep working in day-time